## Sheet1
Proposed Enhancements | Add as enhancement | Developer status
Legend for icons on home page and results page |  | In process per stand up 6/26
Footer at the bottom of the page
Enlarge the font options in the header instead of above the newsfeed
How to Link added to site
No footer at bottom of page
Phones did not react well to scrolling with the map and jumping of data in weird places |  | In process of mobile handling the website
On mobile devices if someone does not want to track their location they will be able to enter zip(state) |  | In Jay's mock up
Option to reutn to shopping list from Results page other than back button (Almost eveyone asked how to get back) |  | Added as enhancement this morning
On Tablet the Search is offset to the almost cut off on the results page - Move to the right more closely to the class so it is not off centered so much
Have the ability to show the events you want to see(Filter) - Many event results |  | Discussed on Friday in stand up
Enlarging the font size is moving up so entire page can be enlarged not just certain text |  | In process per stand up 6/26
UPC lookup
Is Opera going to be supported - Outline what we do support?
On the font size make it more visible which option you are using.
Clear all items from your shopping list |  | In process per stand up 6/26
When deleting an item from your shopping list your are brought back to the top instead of staying where you were in the list.
Save the comments |  | From stand up 6/29